## Gantt Chart w % Complete
Build better gantt charts with TeamGantt for FREE!
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Team Organisation
| Team Meeting | 2020-02-16 | 1 | 2020-02-17 | 2 | 2 | 0 | Nathan | 100%
| Creation of Github Repo | 2020-02-17 | 2 | 2020-02-18 | 2 | 2 | 0 | Meredith | 80%
| Creation of Google Drive | 2020-02-17 | 2 | 2020-02-18 | 2 | 2 | 0 | Brandon | 60%
| Task Allocation | 2020-02-16 | 1 | 2020-02-17 | 2 | 2 | 0 | Michael | 40%
| Code Review Landing Page | 2020-02-19 | 4 | 2020-02-20 | 2 | 0.4 | 1.6 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 9 | 2018-01-12 | 4 | 4 | 0 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 12 | 2018-01-19 | 8 | 6.4 | 1.6 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 17 | 2018-01-19 | 3 | 1.8 | 1.2 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 22 | 2018-01-26 | 5 | 2 | 3 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 15 | 2018-01-19 | 5 | 5 | 0 | Nathan | 100%
| Reserve Room | 2018-01-22 | 22 | 2018-01-23 | 2 | 1.6 | 0.4 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 22 | 2018-01-26 | 5 | 3 | 2 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 26 | 2018-01-29 | 4 | 1.6 | 2.4 | Michael | 40%
| Create Invitations | 2018-01-22 | 22 | 2018-01-25 | 4 | 0.8 | 3.2 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 15 | 2018-01-24 | 10 | 10 | 0 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 25 | 2018-01-30 | 6 | 4.8 | 1.2 | Meredith | 80%
| Update Messaging | 2018-01-24 | 24 | 2018-01-30 | 7 | 4.2 | 2.8 | Michael | 60%
| Publish Calculator | 2018-01-30 | 30 | 2018-01-31 | 2 | 0 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER
Team Organisation
| Initial Team Meeting | 2020-02-16 | 2020-02-17 | 0 | 1 | Everyone
| Task Allocation | 2020-02-17 | 2020-02-18 | 1 | 1 | Everyone
| Creation of Google Drive | 2020-02-18 | 2020-02-19 | 2 | 1 | Bayley
| Creation of Github Repo | 2020-02-18 | 2020-02-19 | 2 | 1 | Jack
Requirements Documentation
| Non-functional requirements | 2020-02-20 | 2020-02-22 | 4 | 2 | Mike
| Functional Requirements | 2020-02-22 | 2020-02-24 | 6 | 2 | Mike
| Domain Requirements & Feasibility Study | 2020-02-24 | 2020-02-27 | 8 | 3 | Mike
| Risk Management | 2020-02-27 | 2020-02-29 | 11 | 2 | Ellis
| Test Plan | 2020-02-29 | 2020-03-02 | 13 | 2 | Ellis
Documentation of Modelling
| Use Case | 2020-03-02 | 2020-03-04 | 15 | 2 | Bayley
| Flowchart | 2020-03-04 | 2020-03-07 | 17 | 3 | Bayley
| Class Diagram | 2020-03-07 | 2020-03-09 | 20 | 2 | Bayley
| Sequence Diagram | 2020-03-08 | 2020-03-10 | 21 | 2 | Bayley
| Graphics / Wireframes | 2020-03-06 | 2020-03-11 | 19 | 5 | Jack
Sprint Cycle 1
| Understanding C# | 2020-02-21 | 2020-03-02 | 5 | 10 | Tom
| Sprint 1 User Stories | 2020-03-01 | 2020-03-03 | 14 | 2 | Jack
| Sprint 1 Task Cards | 2020-03-04 | 2020-03-06 | 17 | 2 | Jack
| Sprint 1 Coding | 2020-03-07 | 2020-03-11 | 20 | 4 | Tom
| Sprint 1 Testing & Documentation | 2020-03-11 | 2020-03-12 | 24 | 1 | Tom/Ellis
Sprint Cycle 2
| Sprint 2 User Stories | 2020-03-13 | 2020-03-15 | 26 | 2 | Jack
| Sprint 2 Task Cards | 2020-03-15 | 2020-03-17 | 28 | 2 | Jack
| Sprint 2 Coding | 2020-03-18 | 2020-03-21 | 31 | 3 | Tom
| Sprint 2 Testing & Documentation | 2020-03-21 | 2020-03-23 | 34 | 2 | Tom/Ellis
Sprint Cycle 3
| Sprint 3 User Stories | 2020-03-23 | 2020-03-25 | 36 | 2 | Jack
| Sprint 3 Task Cards | 2020-03-25 | 2020-03-27 | 38 | 2 | Jack
| Sprint 3 Coding | 2020-03-28 | 2020-04-03 | 41 | 6 | Tom
| Sprint 3 Testing & Documentation | 2020-04-03 | 2020-04-05 | 47 | 2 | Tom/Ellis
Sprint Cycle 4
| Sprint 4 User Stories | 2020-04-06 | 2020-04-08 | 50 | 2 | Jack
| Sprint 4 Task Cards | 2020-04-08 | 2020-04-10 | 52 | 2 | Jack
| Sprint 4 Coding | 2020-04-11 | 2020-04-17 | 55 | 6 | Tom
| Sprint 4 Testing & Documentation | 2020-04-17 | 2020-04-19 | 61 | 2 | Tom/Ellis
Sprint Cycle 5
| Sprint 5 User Stories | 2020-04-20 | 2020-04-22 | 64 | 2 | Jack
| Sprint 5 Task Cards | 2020-04-22 | 2020-04-24 | 66 | 2 | Jack
| Sprint 5 Coding | 2020-04-25 | 2020-04-28 | 69 | 3 | Tom
| Sprint 5 Testing & Documentation | 2020-04-28 | 2020-04-30 | 72 | 2 | Tom/Ellis
Research & Development
| Research into AI Opponents | 2020-03-13 | 2020-03-23 | 26 | 10 | Bayley
| Develop AI techniques | 2020-03-23 | 2020-04-02 | 36 | 10 | Bayley
| Develop Prototype 'Random' AI | 2020-04-02 | 2020-04-12 | 46 | 10 | Bayley
| Develop Prototype 'Smart' AI | 2020-04-12 | 2020-04-22 | 56 | 10 | Bayley
Report
| User Guide / Technical Guide | 2020-04-30 | 2020-05-02 | 74 | 2 | Uknown
| Evaluation | 2020-05-02 | 2020-05-04 | 76 | 2 | Unkown
TeaTea
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")
END DATE = [START DATE]+10
START DATE = [END DATE, row above]+1
START DATE = [END DATE, row above]

## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 2 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 4 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 3 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 2 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 4 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 4 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 8 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 4 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 4 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 4 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 3 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 4 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 2 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 4 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 3 | Rachel | 40%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])